## Gantt Chart
|  |  |  | Today's Date | 2022-02-21 | By: Antonio, Nick, Jennie, Asfand, Jorge, Chris, Taimur
GANTT CHART | [13 empty] | KEY
NOT STARTED
PROJECT TITLE |  | Hudson Valley Audio Visual: Rental System | [5 empty] | ORGANIZATION NAME |  | SUNY New Paltz |  |  |  | IN PROGRESS
PROJECT ADVISOR |  | Anthony Denizard | [5 empty] | DATE |  | 2022-02-05 |  |  |  | COMPLETED
GROUP MEMBERS: Asfand Alavi, Jorge A. Cruz, Jennie Q. Colabella, Antonio Finelli, Nicholas Finelli, Christopher Moschetti, Taimur Tawil, ALL | [13 empty] | Break 3/14-3/18
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | Organizaion Week 2/1/22 | W1 2/7/2022 | W2 2/14/2022 |  | W3 2/21/2022 | W4 3/7/2022 | W5 3/14/22 |  | W6 3/21/22 | W7 3/28/22 | W8 4/4/2022 | W9 4/11/2022 | W10 4/18/2022 | W11 4/25/2022 | W12 5/2/2022 | W13 5/9/2022 | W14 5/16/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.1.1 | Setting up Webex Account | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.2 | Setting up XAMPP / Unreal Engine | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.3 | Assigning Group Leader | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.4 | Client Meeting | Chris | 2022-02-02 | 2022-02-03 | 1 | 100%
1.5 | Decide on Scope of Project | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.6 | Write Project Proposal | Jennie/Chris | 2022-02-04 | 2022-02-04 | 1 | 100%
2 | Groundwork
2.1 | Create first iteration of database | Jennie | 2022-02-05 | 2022-02-14 | 9 | 30%
2.2 | Create design language for UI | Antonio/Taimur | 2022-02-05 | 2022-02-14 | 9 | 0%
2.3 | Create login and register logic | Nick | 2022-02-05 | 2022-02-21 | 16 | 0%
2.4 | Get framework complete for invoicing | Asfand | 2022-02-05 | 2022-02-14 | 9 | 0%
3 | Begin UI Development
3.1 | Implement session handling framework | Chris | 2022-02-07 | 2022-02-21 | 14 | 0%
3.2 | Create calendar UI | Nick/Taimur | 2022-02-09 | 2022-02-21 | 12 | 10%
3.3 | Create calendar logic | Antonio | 2022-02-14 | 2022-02-21 | 7 | 0%
3.4 | Create login / register page | Jorge | 2022-02-16 | 2022-02-21 | 5 | 80%
4 | Develop inventory system
4.1 | Create UI for inventory manipulation | Antonio/Taimur | 2022-02-21 | 2022-02-28 | 7 | 0%
4.2 | Create logic for inventory manipulation | Chris/Antonio | 2022-02-21 | 2022-02-28 | 7 | 0%
4.3 | Implement user permissions with inventory | Asfand | 2022-02-21 | 2022-02-28 | 7 | 0%
4.4 | Create "Shopping Cart" Logic and UI | Jorge/Asfand | 2022-02-21 | 2022-02-28 | 7 | 0%
5 | Develop scheduling system
5.1 | Create UI for scheduling | Asfand/Taimur | 2022-03-07 | 2022-03-14 | 7 | 0%
5.2 | Create logic for schedule manipulation | Antonio | 2022-03-07 | 2022-03-14 | 7 | 0%
5.3 | Create views for schedule | Nick | 2022-03-07 | 2022-03-14 | 7 | 0%
5.4 | Implement schedule approval system | Chris | 2022-03-07 | 2022-03-14 | 7 | 0%
6 | Develop Payment System
6.1 | Implement credit card payment | Taimur | 2022-03-14 | 2022-03-21 | 7 | 0%
6.2 | Implement credit card storage in DB and encryption | Jorge | 2022-03-14 | 2022-03-21 | 7 | 0%
6.3 | Implement UI for scheduling employees | Antonio | 2022-03-14 | 2022-03-21 | 7 | 0%
6.4 | Implement invoice permissions | Nick | 2022-03-14 | 2022-03-21 | 7 | 0%