## Gantt Chart
|  |  |  | Today's Date | 2022-03-14
GANTT CHART | [13 empty] | KEY
NOT STARTED
PROJECT TITLE |  | Hudson Valley Audio Visual: Rental System | [5 empty] | ORGANIZATION NAME |  | SUNY New Paltz |  |  |  | IN PROGRESS
PROJECT ADVISOR |  | Anthony Denizard | [5 empty] | DATE |  | 2022-02-05 |  |  |  | COMPLETED
GROUP MEMBERS: Asfand Alavi, Jorge A. Cruz, Jennie Q. Colabella, Antonio Finelli, Nicholas Finelli, Christopher Moschetti, Taimur Tawil, ALL | [13 empty] | Break 3/14-3/18
Midterm
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | Organizaion Week 2/1/22 | W1 2/7/2022 | W2 2/14/2022 |  | W3 2/21/2022 | W4 3/7/2022 | W5 3/14/22 |  | W6 3/21/22 | W7 3/28/22 | W8 4/4/2022 | W9 4/11/2022 | W10 4/18/2022 | W11 4/25/2022 | W12 5/2/2022 | W13 5/9/2022 | W14 5/16/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.1.1 | Setting up Webex Account | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.2 | Setting up XAMPP / Unreal Engine | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.3 | Assigning Group Leader | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.4 | Client Meeting | Chris | 2022-02-02 | 2022-02-03 | 1 | 100%
1.5 | Decide on Scope of Project | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
1.6 | Write Project Proposal | Jennie/Chris | 2022-02-04 | 2022-02-04 | 1 | 100%
2 | Groundwork
2.1 | Create database version 1 (v1) | Jennie | 2022-02-05 | 2022-02-14 | 9 | 100%
2.2 | Create design language for UI | Antonio/Taimur | 2022-02-05 | 2022-02-14 | 9 | 100%
2.3 | Create login and register logic | Nick/Chris | 2022-02-05 | 2022-02-21 | 16 | 100%
2.4 | Implement class structure on existing code | Chris
3 | Begin UI Development
3.1 | Implement session handling framework (v1) | Chris | 2022-02-07 | 2022-02-21 | 14 | 100%
3.1.1 | Implement session handling framework (v2) | Chris | 2022-02-21 | 2022-02-28 | 7 | 100%
3.1.2 | Connect Session to cart | Chris | 2022-02-22 | 2022-03-01
3.4 | Create login / register page (front end), security issues | Jorge | 2022-02-16 | 2022-02-21 | 5 | 100%
3.4.1 | Create login / register page (back end) | Nick | 2022-02-24 | 2022-03-04 | 10 | 80%
3.5 | Create UI for Z-report
4 | Develop inventory system
4.1 | Create UI for inventory manipulation | Antonio/Taimur | 2022-02-21 | 2022-03-03 | 12 | 100%
4.2 | Create logic for inventory manipulation (v1) | Chris | 2022-02-21 | 2022-02-28 | 7 | 100%
4.2.1 | Create logic for inventory manipulation (v2) | Antonio | 2022-03-07 | 2022-03-14 | 7 | 100%
4.3 | Implement user permissions with inventory | Asfand | 2022-02-25 | 2022-03-04 | 9 | 0%
4.4 | Create "Shopping Cart" Logic | Jorge | 2022-02-21 | 2022-02-28 | 7 | 40%
4.4.1 | Create "Shopping Cart" UI | Jorge | 2022-03-01 | 2022-03-07 | 6 | 0%
4.5 | Database manager: Create database (v2) | Jennie | 2022-02-21 | 2022-02-28 | 7 | 100%
5 | Develop Payment System
5.1 | Get framework complete for invoicing | Asfand | 2022-02-05 | 2022-03-07 | 32 | 80%
5.1.1 | Create invoicing UI | Asfand | 2022-02-28 | 2022-03-07 | 7 | 75%
5.2 | Implement invoice permissions | Nick | 2022-03-14 | 2022-03-21 | 7 | 0%
5.3 | Implement credit card payment | Taimur | 2022-03-14 | 2022-03-21 | 7 | 0%
5.4 | Implement credit card encryption (do NOT store credit cards in db) | Jorge | 2022-03-14 | 2022-03-21 | 7 | 0%
5.5 | Database manager: Create database tables for invoice/payment items | Jennie | 2022-03-07 | 2022-03-14 | 7 | 0%
6 | Develop scheduling system
6.1 | Create calendar UI (On HOLD for now) | Nick/Taimur | 2022-02-09 | 2022-03-04 | 25 | 100%
6.2 | Create UI for scheduling | Taimur | 2022-03-07 | 2022-03-14 | 7 | 0%
6.3 | Create logic for calendar/schedule manipulation | Antonio | 2022-03-07 | 2022-03-14 | 7 | 0%
6.4 | Create views for schedule | Nick | 2022-03-07 | 2022-03-14 | 7 | 0%
6.5 | Implement schedule approval system | Chris | 2022-03-07 | 2022-03-14 | 7 | 0%
6.6 | Implement UI for scheduling employees | Antonio | 2022-03-14 | 2022-03-21 | 7 | 0%
7 | MIDTERM PRESENTATION: Topics
7.1 | Write script for 4 minute video presentation | Jennie | 2022-02-28 | 2022-03-04 | 4 | 100%
7.2 | Login, error handling; Paperwork: flowcharts | Nick | 2022-02-28 | 2022-03-06 | 6 | 70%
7.4 | Inventory (search, add and delete products); Paperwork: flowcharts | Antonio | 2022-02-28 | 2022-03-06 | 6 | 80%
7.5 | Shopping cart; Paperwork: flowchart | Jorge | 2022-02-28 | 2022-03-06 | 6 | 80%
7.6 | Invoicing; Paperwork: flowchart | Asfand | 2022-02-28 | 2022-03-06 | 6 | 90%
7.3 | Sessions (possible showing home page); Paperwork: flowcharts | Chris | 2022-02-28 | 2022-03-06 | 6 | 75%
7.7 | Database; Paperwork: flowcharts | Jennie | 2022-02-28 | 2022-03-06 | 6 | 70%
7.8 | Home page (navbar, cart styling, UI for calendar). Will record segment and send to Jennie on Tuesday. Paperwork: flowcharts | Taimur | 2022-02-28 | 2022-03-06 | 6 | 70%
8 | ADA Requirements
8.1 | ADA compliance: need tool tip for blind users if their mouse rolls over a tip box the program will read the tip
8.2
9 | Security
9.1 | ADA compliance: need tool tip for blind users if their mouse rolls over a tip box the program will read the tip
9.2