## Gantt Chart
|  |  |  | Today's Date | 2022-03-31
GANTT CHART | [13 empty] | KEY
[14 empty] | NOT STARTED |  | POS Requirement
PROJECT TITLE |  | Audio Visual: Rental System | [5 empty] | ORGANIZATION NAME |  | SUNY New Paltz |  |  |  | IN PROGRESS
PROJECT ADVISOR |  | Anthony Denizard | [5 empty] | DATE |  | 2022-02-05 |  |  |  | COMPLETED |  | Prep Final Pres
GROUP MEMBERS: Asfand Alavi, Jorge A. Cruz, Jennie Q. Colabella, Antonio Finelli, Nicholas Finelli, Taimur Tawil, ALL (Christopher Moschetti) | [13 empty] | Break 3/14-3/18 |  | Final Pres Week
[14 empty] | Midterm |  | Final
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | Organizaion Week 2/1/22 | W1 2/7/2022 | W2 2/14/2022 |  | W3 2/21/2022 | W4 3/7/2022 | W5 3/14/22 |  | W6 3/21/22 | W7 3/28/22 | W8 4/4/2022 | W9 4/11/2022 | W10 4/18/2022 | W11 4/25/2022 | W12 5/2/2022 | W13 5/9/2022 | W14 5/16/2022
A | Project Conception and Initiation
A.1 | Setting up Github | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.1.1 | Setting up Webex Account | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.2 | Setting up XAMPP / Unreal Engine | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.3 | Assigning Group Leader | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.4 | Client Meeting | Chris | 2022-02-02 | 2022-02-03 | 1 | 100%
A.5 | Decide on Scope of Project | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.6 | Write Project Proposal | Jennie/Chris | 2022-02-04 | 2022-02-04 | 1 | 100%
B | Groundwork
B.1 | Create database | Jennie | 2022-02-05 | 2022-02-14 | 9 | 100%
B.2 | Create design language for UI | Antonio/Taimur | 2022-02-05 | 2022-02-14 | 9 | 100%
B.3 | Create POS Program Organization Framework Document | Antonio/Nick | 2022-02-01 | 2022-02-05 | 4 | 100%
C | Management
C.1 | Manage Github | Antonio/Nick | 2022-02-01 | 2022-05-16 | 105 | 100%
C.2 | Mangage Group | Jennie | 2022-02-15 | 2022-05-16 | 91
1 | Develop Inventory System (POS REQUIREMENT 1)
1.1 | Create UI for inventory manipulation | Antonio/Taimur | 2022-02-21 | 2022-03-03 | 12 | 100%
1.2 | Create logic for inventory manipulation Add Remove Update(v1) | Chris | 2022-02-21 | 2022-02-28 | 7 | 100%
1.2.1 | Create logic for inventory manipulation Wrote Search, Modified Update, Wrote Js for procedurally filling out forms, Front End Integration (v2) | Antonio | 2022-03-07 | 2022-03-14 | 7 | 100%
1.2.2 | Searching logic classed out for future implementation in other DB access | Antonio | 2022-03-21 | 2022-03-28 | 7 | 100%
1.3 | Create relational database table for inventory/products | Jennie | 2022-03-07 | 2022-03-14 | 7 | 100%
1.4 | Implement error handling for all db access classes/forms | Nick | 2022-03-14 | 2022-03-24 | 10 | 100%
1.6 | Add additional search functionality (Search all columns at once) | Antonio | 2022-03-21 | 2022-03-28 | 7 | 100%
2 | Create Vendor System (POS REQUIREMENT 2)
2.1 | Create relational database table for Vendors | Jennie | 2022-03-14 | 2022-03-21 | 7 | 100%
3 | Create Transaction System (POS REQUIREMENT 3)
3.1 | Create event order UI | Taimur | 2022-04-02 | 2022-04-15 | 13 | 0%
3.2 | Create event order logic | Taimur | 2022-03-21 | 2022-04-01 | 10 | 85%
3.3 | Connect calendar to event order | Taimur | 2022-04-16 | 2022-04-23 | 7 | 0%
3.4 | Create relational database table for event orders | Jennie | 2022-03-07 | 2022-03-16 | 9 | 100%
4 | Create Storage for Customer/Client Accounts (POS REQUIREMENT 4)
4.1 | Create relational database table for Clients | Jennie | 2022-02-05 | 2022-02-12 | 7 | 100%
5 | Develop Sales/Shopping Cart/Invoice system (POS REQUIREMENT 5)
5.1 | Create relational database tables for invoice | Jennie | 2022-02-21 | 2022-02-28 | 7 | 100%
5.2 | Create "Shopping Cart" Logic | Jorge | 2022-02-21 | 2022-02-28 | 7 | 100%
5.3 | Create "Shopping Cart" UI | Jorge | 2022-03-14 | 2022-03-28 | 14 | 95%
5.4 | Get framework complete for invoicing | Asfand | 2022-02-05 | 2022-03-07 | 32 | 100%
5.4.1 | Create invoicing UI | Asfand | 2022-03-21 | 2022-03-25 | 4 | 95%
5.5 | Implement invoice permissions | Nick | 2022-03-14 | 2022-03-21 | 7 | 80%
5.6 | Implement credit card payment | Taimur | 2022-03-14 | 2022-03-21 | 7 | 0%
5.7 | Implement credit card encryption (do NOT store credit cards in db) | Jorge | 2022-03-21 | 2022-04-04 | 13 | 35%
5.8 | Integrate Invoicing System into main | Asfand | 2022-04-01 | 2022-04-08 | 7 | 0%
5.9 | Integrate cart into main | Jorge | 2022-04-01 | 2022-04-08 | 7 | 0%
MIDTERM PRESENTATION: Topics
7.1 | Write script for 4 minute video presentation | Jennie | 2022-02-28 | 2022-03-04 | 4 | 100%
7.2 | Login, error handling; Paperwork: flowcharts | Nick | 2022-02-28 | 2022-03-06 | 6 | 100%
7.4 | Inventory (search products); Paperwork: flowcharts | Antonio | 2022-02-28 | 2022-03-06 | 6 | 100%
7.5 | Shopping cart; Paperwork: flowchart | Jorge | 2022-02-28 | 2022-03-06 | 6 | 100%
7.6 | Invoicing; Paperwork: flowchart | Asfand | 2022-02-28 | 2022-03-06 | 6 | 100%
7.3 | Sessions, add/remove/edit employees+products, Project Use Case: flowcharts, integrate code versions, Integrate code versions into one working project, refactor for ease of use | Chris | 2022-02-28 | 2022-03-06 | 6 | 100%
7.7 | Database; Paperwork: flowcharts | Jennie | 2022-02-28 | 2022-03-06 | 6 | 100%
7.8 | Home page (navbar, cart styling, UI for calendar). Will record segment and send to Jennie on Tuesday. Paperwork: flowcharts | Taimur | 2022-02-28 | 2022-03-06 | 6 | 100%
6 | Service System (POS REQUIREMENT 6, complete If applicable)
6.1 | Create relational database tables for services (N/A)
7 | Develop Employee Storage System (POS REQUIREMENT 7)
7.1 | Create employee login / register page (front end) | Jorge | 2022-02-16 | 2022-02-21 | 5 | 100%
7.2 | Create employee login (back end) Register, login, remove, update | Chris | 2022-02-24 | 2022-03-21 | 27 | 100%
7.3 | Clock employee time (N/A)
8 | Financial Requirements (POS REQUIREMENT 8)
8.1 | Meet Financial Regulatory Compliance | Jorge/Asfand/Jennie | 2022-03-17 | 2022-05-01 | 44 | 25%
8.2 | Create UI for Z-report | Jennie | 2022-04-01 | 2022-04-14 | 13 | 0%
8.2.1 | Create printable Z-report includes type of sale (cash, credit,purchase order...), total sales, sales by employee), total and type of refunds (total cash sales for the day, total credit sales for the day, total cash refunds, total credit card refunds), Total cash at start and end of day for drawers | Jennie | 2022-04-07 | 2022-05-01 | 24 | 0%
8.2.2 | Reports choices: group reports to match sales tax calendar of payments
8.2.3 | Create profit and loss reports | Jennie | 2022-04-07 | 2022-05-01 | 24 | 0%
9 | Security System Requirements (POS REQUIREMENT 9)
9.1 | Meet Financial Regulatory Compliance Security Regulations | Jorge/Asfand/Jennie | 2022-03-17 | 2022-05-01 | 44 | 25%
9.2 | ADA compliance: ex. Add tip boxes that give suggestions for navigating the program. To make it ADA compliant for blind users, make sure the program reads the text if their mouse rolls over a tip box. | Nick/Antonio | 2022-03-21 | 2022-04-29 | 7 | 85%
9.2.1 | Inventory page ADA compliance | Antonio Finelli | 2022-03-25 | 2022-04-04 | 10 | 80%
9.3 | Create API or mock code to connect to online credit card and check handling (the connection will have to be done at a later date) | Jorge/Asfand | 2022-03-21 | 2022-03-28 | 7 | 5%
9.4 | Safe guarding any customer data stored for marketing | Nick/Antonio | 2022-03-17 | 2022-05-01 | 44 | 85%
9.5 | Secure login system for employees (login and register logic) | Nick/Chris | 2022-02-05 | 2022-02-21 | 16 | 100%
9.6 | If built as a cloud based POS, security measures needed by hosting server | Nick/Antonio | 2022-03-17 | 2022-05-01 | 44 | 85%
9.7 | Session configuration to allow users to stay logged in from page to page | Chris/Nick | 2022-02-07 | 2022-02-21 | 14 | 100%
9.7.2 | Implement session handling framework (v2) | Chris | 2022-02-21 | 2022-02-28 | 7 | 100%
9.8 | Password security (they have to be encrypted) | Jorge | 2022-03-21 | 2022-04-07 | 7 | 80%
9.9 | Implement framework for class based methods/db access | Nick/Antonio | 2022-03-31 | 2022-05-01 | 31 | 85%
10 | Develop scheduling system
10.1 | Create calendar UI | Nick/Taimur | 2022-02-09 | 2022-03-10 | 31 | 100%
10.2 | Create UI for scheduling | Taimur | 2022-03-07 | 2022-04-22 | 45 | 0%
10.5 | Implement schedule approval system sessions | Nick | 2022-04-04 | 2022-04-28 | 24 | 0%
11 | Documentation and Testing
11.1 | Normalize database | Jennie | 2022-03-21 | 2022-03-26 | 5 | 10%
11.2 | Write user guide
11.3 | Do program testing | ALL
11.4 | Verify database meets language standards (no reserved words, etc.) | Jennie | 2022-03-21 | 2022-03-26 | 5 | 10%
11.5 | Full project Use case
12 | Forms
12.1 | Create client form | Antonio | 2022-04-01 | 2022-04-28 | 27 | 0%
12.2 | Create employee form | Antonio | 2022-04-01 | 2022-04-28 | 27 | 0%
12.3 | Create vendor form | Antonio | 2022-04-01 | 2022-04-28 | 27 | 0%
12.4 | Create mailing list form | Antonio | 2022-04-01 | 2022-04-28 | 27 | 0%
12.5 | Create feedback form | Antonio | 2022-04-01 | 2022-04-28 | 27 | 0%
FINAL PRESENTATION: Topics