## Gantt Chart
|  |  |  | Today's Date | 2022-05-04
GANTT CHART | [13 empty] | KEY
[14 empty] | NOT STARTED |  | POS Requirement
PROJECT TITLE |  | Audio Visual: Rental System | [5 empty] | ORGANIZATION NAME |  | SUNY New Paltz |  |  |  | IN PROGRESS
PROJECT ADVISOR |  | Anthony Denizard | [5 empty] | DATE |  | 2022-02-05 |  |  |  | COMPLETED |  | Prep Final Pres
GROUP MEMBERS: Asfand Alavi, Jorge A. Cruz, Jennie Q. Colabella, Antonio Finelli, Nicholas Finelli, Taimur Tawil, Christopher Moschetti | [13 empty] | Break 3/14-3/18 |  | Final Pres Week
[14 empty] | Midterm |  | Final
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | Organizaion Week 2/1/22 | W1 2/7/2022 | W2 2/14/2022 |  | W3 2/21/2022 | W4 3/7/2022 | W5 3/14/22 |  | W6 3/21/22 | W7 3/28/22 | W8 4/4/2022 | W9 4/11/2022 | W10 4/18/2022 | W11 4/25/2022 | W12 5/2/2022 | 5/5/2022 FINAL 5/9/22 Classes End
A | Project Conception and Initiation
A.1 | Setting up Github | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.1.1 | Setting up Webex Account | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.2 | Setting up XAMPP / Unreal Engine | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.3 | Assigning Group Leader | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.4 | Client Meeting | Chris | 2022-02-02 | 2022-02-03 | 1 | 100%
A.5 | Decide on Scope of Project | ALL | 2022-02-01 | 2022-02-05 | 4 | 100%
A.6 | Write Project Proposal | Jennie/Chris | 2022-02-04 | 2022-02-04 | 1 | 100%
B | Groundwork
B.1 | Create database | Jennie | 2022-02-05 | 2022-02-14 | 9 | 100%
B.2 | Create design language for UI | Antonio/Taimur | 2022-02-05 | 2022-02-14 | 9 | 100%
B.3 | Create POS Program Organization Framework Document | Antonio/Nick | 2022-02-01 | 2022-02-05 | 4 | 100%
C | Management
C.1 | Manage Github | Antonio/Nick | 2022-02-01 | 2022-05-16 | 105 | 100%
C.2 | Mangage Group | Jennie | 2022-02-15 | 2022-05-16 | 91 | 100%
1 | Develop Inventory System (POS REQUIREMENT 1)
1.1 | Create UI for inventory manipulation | Antonio/Taimur | 2022-02-21 | 2022-03-03 | 12 | 100%
1.2.1 | Create logic for inventory manipulation Wrote Search, Modified Update, Wrote Js for procedurally filling out forms, Front End Integration | Antonio | 2022-03-03 | 2022-03-17 | 14 | 100%
1.2.2 | Searching logic classed out for future implementation in other DB access | Antonio | 2022-03-18 | 2022-03-28 | 10 | 100%
1.3 | Create relational database table for inventory/products | Jennie | 2022-03-07 | 2022-03-14 | 7 | 100%
1.4 | Implement error handling for all db access classes/forms | Nick | 2022-03-22 | 2022-04-04 | 12 | 100%
1.5 | Implement DB access for different tables | Antonio | 2022-03-28 | 2022-04-11 | 4 | 100%
1.6 | Add additional search functionality (Search all columns at once) | Antonio | 2022-03-21 | 2022-03-28 | 4 | 100%
2 | Create Vendor System (POS REQUIREMENT 2)
2.1 | Create relational database table for Vendors | Jennie | 2022-03-14 | 2022-03-21 | 7 | 100%
2.2 | Create vendor form to add/manage vendors | Antonio | 2022-04-07 | 2022-04-14 | 7 | 100%
3 | Create Transaction System between Vendors/Clients if applicable (POS REQUIREMENT 3)
3.1 | Transactons between vendors and clients (N/A) |  |  |  |  | N/A
4 | Create Storage for Customer/Client Accounts (POS REQUIREMENT 4)
4.1 | Create event order UI | Taimur | 2022-04-04 | 2022-04-15 | 11 | 100%
4.2 | Create relational database table for event orders | Jennie | 2022-03-07 | 2022-03-16 | 9 | 100%
4.3 | Create event order logic | Taimur | 2022-03-28 | 2022-04-07 | 9 | 100%
4.4 | Connect calendar to event order | Taimur | 2022-04-16 | 2022-04-23 | 7 | 100%
4.5 | Create relational database table for Clients | Jennie | 2022-02-05 | 2022-02-12 | 7 | 100%
4.6 | Create Client form to add/manage clients | Antonio Finelli | 2022-04-14 | 2022-04-28 | 14 | 100%
5 | Develop Sales/Shopping Cart/Invoice system (POS REQUIREMENT 5)
5.1 | Create relational database tables for invoice | Jennie | 2022-02-21 | 2022-02-28 | 7 | 100%
5.2 | Create "Shopping Cart" Logic | Jorge | 2022-02-21 | 2022-02-28 | 7 | 100%
5.3 | Create "Shopping Cart" UI | Jorge | 2022-03-14 | 2022-03-28 | 14 | 100%
5.4 | Get framework complete for invoicing | Asfand | 2022-02-05 | 2022-03-07 | 32 | 100%
5.4.1 | Create invoicing UI | Asfand | 2022-03-21 | 2022-03-25 | 4 | 100%
5.5 | Implement invoice permissions | Nick | 2022-03-31 | 2022-04-28 | 28 | 100%
5.6 | Implement credit card encryption (do NOT store credit cards in db) | Jorge | 2022-03-21 | 2022-04-29 | 38 | 100%
5.7 | Integrate Invoicing System into main | Asfand | 2022-04-14 | 2022-04-28 | 14 | 100%
5.8 | Integrate cart into main | Jorge/ Nick | 2022-04-14 | 2022-04-29 | 15 | 100%
5.9 | Refund page | Asfand/Nick | 2022-04-18 | 2022-05-01 | 13 | 100%
6 | Service System (POS REQUIREMENT 6, complete If applicable)
6.1 | Create relational database fields for services (N/A) |  |  |  |  | N/A
7 | Develop Employee Storage System (POS REQUIREMENT 7)
7.1 | Create employee login / register page (front end) | Jorge | 2022-02-16 | 2022-02-21 | 5 | 100%
7.12 | Create employee login (back end) Register, login, remove, update | Chris | 2022-02-24 | 2022-03-21 | 27 | 100%
7.2, 7.3 | Manage personnel info. and clock employee time if payroll is part of system (N/A) |  |  |  |  | N/A
7.4 | Track employee sales (Only manager takes orders, so not applicable to this client.) (N/A) |  |  |  |  | N/A
7.5 | Create employee form to add/manage employees | Antonio Finelli | 2022-04-25 | 2022-04-27 | 2 | 100%
8 | Financial Requirements (POS REQUIREMENT 8)
8a | Meet Financial Regulatory Compliance | Jorge/Asfand/Jennie | 2022-03-17 | 2022-05-01 | 44 | 100%
8.1 | Create UI for Z-report | Jennie | 2022-04-01 | 2022-04-14 | 13 | 100%
8.1.2 | Create printable Z-report includes type of sale (cash, credit,purchase order...), total sales, sales by employee), total and type of refunds (total cash sales for the day, total credit sales for the day, total cash refunds, total credit card refunds), Total cash at start and end of day for drawers | Jennie | 2022-04-07 | 2022-05-01 | 24 | 100%
8.2 | Reports choices: group reports to match sales tax calendar of payments | Jennie | 2022-04-21 | 2022-05-01 | 24 | 100%
8.3 | Create profit and loss reports | Jennie | 2022-04-07 | 2022-05-01 | 24 | 100%
9 | Security System Requirements (POS REQUIREMENT 9)
9.1 | Meet Financial Regulatory Compliance Security Regulations | Jorge/Asfand/Jennie | 2022-03-21 | 2022-04-14 | 23 | 100%
9.2 | ADA compliance: ex. Add tip boxes that give suggestions for navigating the program. To make it ADA compliant for blind users, make sure the program reads the text if their mouse rolls over a tip box. | Nick/Antonio | 2022-03-21 | 2022-04-07 | 7 | 100%
9.2.1 | Inventory page ADA compliance | Antonio Finelli | 2022-03-25 | 2022-04-04 | 10 | 100%
9.3 | Create API or mock code to connect to online credit card and check handling (the connection will have to be done at a later date) | Jorge/Asfand | 2022-03-21 | 2022-04-14 | 23 | 100%
9.3.1 | Create API credentials creation page | Asfand | 2022-03-21 | 2022-04-14 | 23 | 100%
9.4 | Safe guarding any customer data stored for marketing | Nick/Antonio | 2022-03-21 | 2022-04-07 | 7 | 100%
9.5 | Secure login system for employees (login and register logic) | Nick/Chris | 2022-02-05 | 2022-02-21 | 16 | 100%
9.6 | If built as a cloud based POS, security measures needed by hosting server | Jorge | 2022-03-31 | 2022-04-25 | 31 | 100%
9.7 | Session configuration to allow users to stay logged in from page to page | Chris/Nick | 2022-02-07 | 2022-02-21 | 14 | 100%
9.7.2 | Implement session handling framework (v2) | Chris | 2022-02-21 | 2022-02-28 | 7 | 100%
9.7.3 | Create API credentials update page | Asfand | 2022-04-15 | 2022-05-01 | 16 | 100%
9.8 | Password security (they have to be encrypted) | Jorge | 2022-03-21 | 2022-03-28 | 7 | 100%
9.9 | Implement framework for class based methods/db access | Nick/Antonio | 2022-03-31 | 2022-04-25 | 31 | 100%
10 | Develop scheduling system
10.1 | Create calendar UI | Nick/Taimur | 2022-02-09 | 2022-03-10 | 31 | 100%
10.2 | Create UI for scheduling | Taimur | 2022-03-07 | 2022-03-14 | 7 | 100%
10.3 | Implement schedule approval system sessions | Nick | 2022-04-07 | 2022-04-14 | 7 | 100%
11 | Documentation and Testing
11.1 | Normalize database | Jennie | 2022-03-21 | 2022-04-14 | 23 | 100%
11.2 | Verify database meets language standards (no reserved words, etc.) | Jennie | 2022-03-21 | 2022-04-07 | 16 | 100%
11.4 | Do program testing | Nick | 2022-03-21 | 2022-04-07 | 16 | 100%
11.5 | Put sources on our about page | Taimur | 2022-04-12 | 2022-04-21 | 9 | 100%
11.6 | Mobile responsiveness | Taimur, Antonio | 2022-03-21 | 2022-04-07 | 16 | 100%
12 | Forms/Funtions to add if time permits
12.1 | Create mailing list form
12.2 | Create feedback form
MIDTERM PRESENTATION: Topics
M.1 | Write script for 4 minute video presentation | Jennie | 2022-02-28 | 2022-03-04 | 4 | 100%
M.2 | Login, error handling; Paperwork: flowcharts | Nick | 2022-02-28 | 2022-03-06 | 6 | 100%
M.3 | Inventory (search products); Paperwork: flowcharts | Antonio | 2022-02-28 | 2022-03-06 | 6 | 100%
M.4 | Shopping cart; Paperwork: flowchart | Jorge | 2022-02-28 | 2022-03-06 | 6 | 100%
M.5 | Invoicing; Paperwork: flowchart | Asfand | 2022-02-28 | 2022-03-06 | 6 | 100%
M.6 | Sessions, add/remove/edit employees+products, Project Use Case: flowcharts, integrate code versions | Chris | 2022-02-28 | 2022-03-06 | 6 | 100%
M.7 | Database; Paperwork: flowcharts | Jennie | 2022-02-28 | 2022-03-06 | 6 | 100%
M.8 | Home page (navbar, cart styling, UI for calendar). Will record segment and send to Jennie on Tuesday. Paperwork: flowcharts | Taimur | 2022-02-28 | 2022-03-06 | 6 | 100%
FINAL PRESENTATION: Topics
| 10 minute (minimum) video presentation | ALL
| Flowcharts | ALL